- 10/11 iCampus Mtg

- Tuesday, October 11, 2005

- 9:01 AM

- Agenda

- The goals for this meeting is to:

- Review goals for iCampus project we are engaged with

  - iLabs Budget

  - XMAS

  - Others

- Review assessment study proposal

- Review Communication Plan for iCampus

- Complete Outreach Proposal and Budget

- Becky's List

- Define JSC Meeting Agenda

- Financial Forecast through 2006

- Projects	Budget

- Faculty RFP	$600K

- iLabs		$1,284K

- Comm		$258K

- Outreach	$817K

- JSC Agenda

- Date: Tuesday, November 1st

- Room: 32-D507

- Dinner: Oak room Copley Plaza

- Hal is gone from 9:30-11AM

- Start time 11:00 AM

- Goals:

- Approve iLabs proposal & Budget ($1,284K)

- Approve Outreach Proposal & Budget ($1,075K)

  - Includes communication budget.

  - Assessment Plans

- Approve Faculty RFP ($600K)

  - Need to know who to invite to present to the JSC

  - Project A

  - Project B

- Project Reviews ?

  - iLabs

  - iDAT

  - iGEM

- Capstone Event

  - Marsha available?

- Other?

- Outreach

- Looking at $1.4M Budget

- Broken down into 5 Specific project

- iLabs ($216K)

  - $20K - Improving iLabs Web Site

  - $15K - Sloan, SUNY support, build iLabs implementation

  - $30K - PRC workshop

  - $50K - Consortium Development

  - $1K - Telcom Charges

  - - ($100K) 2 MIT labs moved to iLabs budget.

  - $100K - Remote Labs Conference

    - Paying for 6-8 Hub participates (T&E)

- iMoat ($25K)

  - $1K - Develop instructional videos

  - $22K - iMoat Mtg

  - $2K - 4C meeting in Chicago in March

- xTutor ($67K)

  - $22K - 1 TA Support for 6.034 &  6.004;

  - $20K - 3 months of Staff Developer

  - $05K - SMIL development

  - $20K - xTutor User Mtg

- TEAL ($35K)

  - $25K - Curriculum development TEALsim?

    - Development of problem sets for EM

  - $3K - CD production

  - $7K - TEAL Workshop

- XMAS ($58.3K)

  - $23K - Simplify first time experience - Development

  - $5K - Public XMAS server

  - $10K - 2 user group Mtg

  - $20K - XMAS Conf.

- Other -

  - $20K for application release engineering.

- Community Build

- Seed Grants

  - $230K

- Regional Hub Mtg Support

  - $120K

- MISTI

  - $105K

- Assessment

  - CLP

    - $20K promised

  - iLabs

    - $27K Rudy and Judy- has it been paid already?

  - iLabs Economic Model

    - $10K

- iCampus Cap Stone Event

- Projects

- iLabs

- iMoat

- Visualizing Cultures

- TEAL

- Assessment Study

- Received a proposal for $225K from TLL (i.e. Ehrmann, Gilbert, Zuniga)

- The number of interviews will effect the budget the most.

- Budgeted

- 4 US trips

- Study 9 Projects

- An average of 14 interviews/Projects (i.e. 126 interviews)

- List of project that need to be Interviewed

| Projects | Successful | Failed | Interview at MIT | Interview Other | Comments |
| --- | --- | --- | --- | --- | --- |
| iLabs | Yes |  | 4 Faculty, 3 Developers | 2 Faculty, 2 Developers | Talk to Tec and Cambridge and UQ |
| iMoat | Yes |  | Les Perlman, Chris Felknor | Rice (2), CalTech (2), LSU (2) |  |
| xTutor V1 | Maybe |  | Tomas, EricG, Albert Meyer, Chris T | URI(2), UQ(2), NE(2) | Grab MIT curriculum and use it. |
| TEAL | Yes |  | John B, Mark K, Peter D, (New John B) | CCU(2), WPI(2), NCSU (Beichner) |  |
| Fluids |  | Yes | Dick Yue, CC Mei, Heidi Nef | NA |  |
| MechE |  | Yes | Mary B, Sanjay Sarman, Department Head, Developer? | NA | Department Supported, why did it fail… |
| Total |  |  | 25 | 23 | 12 institutions, 4 international |

- XMAS

- Asked for $58K

- Has spent out its $60K budget, is asking for additional funds

- Will need to be part of the outreach budget...

- iLabs Budget

- Total		Outreach

- iLabs Arch		$ 514,938

- iLabs@MIT		$ 581,928

- Lab View		$ 356,849

- Open iLabs		$ 49,648	$ (49,648)

- Consuortium		$ 170,780 	$ (170,780)

- Assessment		$ -

- Other Dissemination	$ -

- Total			$ 1,674,143 	$ (220,428)

- iLabs Research 	$ 1,453,715

- iLabs@MIT we added overhead, increasing it by $175K

- Communication Plan

- Communication Goals

- Both Microsoft and MIT conclude that iCampus was a positive collaboration with valuable results

- Selected projects highlight impact both at MIT and around the world. This is the beginning of a movement of open source tool sharing.

- We have valuable tools and resources in place for hubs to adapt and use.

- Microsoft/MIT alliance is a significant part of MIT’s success in using educational technology to promote effective teaching and learning

- There is a path to sustainability at MIT for projects that have made a difference and have value, including iCampus projects

- The iCampus project and values are inclusive of students: over $1 MM was granted to MIT students

- MIT faculty and Affiliates are informed and using iCampus projects

- iCampus projects are known and used outside of MIT

- Recognition of MIT partnership international to support active learning, web services and open source solutions for educational technology

- MIT and Microsoft build communities of practiced for educational technologies.

- Budget: ($258K)

- $021K - Material for the Hubs (Demo is 20K)

- $001K - Branding Strategy

- $026K - Web site updates

- $130K - Event - Capstone Event

- $001K - MIT Museum

- $078K - Other