## Sheet1
iCampus Communications: Details
Timetable, Budget and Responsible Parties
Audiences | Communications Vehicles | Details | Timeframe | Budget est. | Responsible Party
Everyone | Web site (iCampus and hub portal) | iCampus general - new content/design udate | 3 months | $ 10k | Bob Wilkes/Hecht
|  | - update outdated content |  | $ 3k | temp - hourly basis
|  | Outreach portal - new content/design update | 3 months | $ 10k | Bob Wilkes/Hecht
|  | Resources - template for hub home pages | By 10/19 | $ 3k | Marsha/PSB (templates)
|  | - PowerPoint template |  |  | Marsha
|  | - logos, boilerplate |  |  | Marsha
|  | - handouts, legal documents |  |  | Marsha
|  | - community forums |  |  | Phil
|  | - case studies |  |  | Marsha
|  | - style guide for graphics |  |  | Marsha
|  | - demos |  | $ 30k | PIs, Paul
Universities -- US, ROW | Public relations | Event driven - "newsworthy" (iGem) | Ongoing |  | Marsha with Patti Richards,
|  | Projects - iLabs | Ongoing |  | Wagged (Andrushat?)
|  | Conclusion event - impact, Chronicle | Fall 2006
| Branding strategy | Develop branding strategy for hubs, affiliates | Fall 2006 | $ 1k | Marsha/PSB (logo variation)
| Speaking opportunities (e.g. Educause) | Ongoing - primarily Phil's presentations | Ongoing |  | Phil, Hal
Involve others from hubs in future
Microsoft (define?) | Communication to MS employees | Final report to Bill Gates; MS internal newsletter | Fall 2006 |  | Final report - team
MIT community | MIT spotlight, Tech Talk, MIT Fac Newsletter
(MITCET charge) | MITCET agenda | Work into MITCET meetings and work groups | AY 2005-06 |  | Hal
| Event, Fall 2006 | Define scope of event (n=200); projects/tracks | Kick-off 12/05 | $100 - 200k | Team
Faculty at MIT | Rounds to departments (internal) | Presentations by Hal | Spring 2006 |  | Hal
(MITCET charge) | Site visits (external) |  |  |  | Phil
Faculty at other schools | MIT Museum (both) | Timed to correspond with Syllabus Conference | June-July 2006 |  | Elisabeth, Phil, Marsha
| iCampus Newsletter (both) | Revisit purpose, content, mailing list | 2 months |  | Content - Phil;
| Evangelists (external) | Need to develop evangelists |  |  | - template, layout - Marsha
Faculty at MIT using iCampus | Resources: contact info, materials, | See hub resources for list |  |  | Marsha
projects and/or tools | boilerplate, style guide, demos, logos, etc.
Faculty at other schools | Project workshops | Similar to iLabs Workshop at MIT |  |  | PIs, Phil
Existing hubs and affiliates | Process and support to build an iCampus |  |  |  | Phil, team
community (not a communications task)
Marsha Sanders, iCampus Communications Details, October 9, 2006